# TotalRecalls Launch — Artifact Topics & Gap Analysis

Built 2026-09-29 from the 105 canvas artifacts (99 original + 6 captured later:

Missing Items Checklist, YT 3, YT 4, YT 5 V2, plus Video 5 download).

Source of truth for "planned" = Jasper's own docs: Launch Marketing Plan (Revised, 72b37216),

Master Implementation Plan (904ecc99), Launch Gap Checklist (e35b3e71), Missing Items

Checklist (9bb2daab), 60-Day Content Calendar (f985590b), YouTube 10-Video Plan (baee6adf).

# 1. Inventory by topic

## Strategy / Plans / Checklists (11)

| Doc | Notes |
| --- | --- |
| TotalRecalls Master Implementation Plan (904ecc99) | **Complete** — day-by-day execution table Days -7→45, owners blank |
| TotalRecalls Master Implementation Plan (26de1acc) | TRUNCATED duplicate of the above (5.2k vs 16k) — delete |
| TotalRecalls Launch Marketing Plan Revised (72b37216) | Complete — the channel/strategy master |
| TotalRecalls Launch Marketing Plan Revised (6f06cdb1) | TRUNCATED draft — delete |
| TotalRecalls Launch Readiness Plan (b5862862) | Infrastructure checklist |
| TotalRecalls Launch Gap Checklist (e35b3e71) | Earlier gap analysis (superseded by Missing Items) |
| TotalRecalls Missing Items Checklist (9bb2daab) | **Jasper's own latest status tracker** — use as base for requests |
| TotalRecalls Launch Marketing Organization (794587e3) | Original org doc |
| TotalRecalls Launch Campaign (fd6f04ea) | Campaign brief |
| TotalRecalls 60-Day Launch Content Calendar (f985590b) | Blog/guide schedule Days 1–45 |
| Landing Page.md | (stray, from earlier export) |

## YouTube — Channel & Production (10)

YouTube Content Plan: First 10 Videos (baee6adf) · YouTube Channel Description (99102005) ·

Playlist Structure & Naming (e1aaa6d7) + Playlist Structure System (f56207c7, near-dup) ·

YouTube Upload Checklist & Template (ae24a5cf) · Thumbnail Concepts (24ac5bf4) ·

Main Product Explainer Video Outline (d7fccd92) · Video Shot List (3006c005) ·

Video Storyboard (702707c6) · Short-Form Video Strategy (ccb00150)

## YouTube — Scripts (the 10-video plan)

| # | Title (from plan) | Status |
| --- | --- | --- |
| 1 | Save AI Chats from 8 Providers to One Folder | ✅ complete (18d7057b) |
| 2 | Why I Built TotalRecalls | ✅ complete (df0b43e0) |
| 3 | You're Not Backing Up Your AI Chats (Short) | ✅ complete **V2** (jasper_docs, 8,875 chars) — v1 (ddb08473) was truncated, superseded |
| 4 | How to Export ChatGPT Conversations to Markdown | ✅ complete (28ea0bf2) |
| 5 | Back Up Your Claude Chat History Locally | ✅ complete V2 (downloaded) |
| 6 | Trying to Get Your Old AI Conversations Back? Good Luck (Short) | ⚠️ **downloaded mid-generation** (3,251 chars, ends mid-sentence in Scene 3) — re-download after "completed" |
| 7 | Save Perplexity and Gemini Threads You Can Actually Read | ✅ complete **V3** (jasper_docs, 15,867 chars) — V1/V2 were both truncated, superseded |
| 8 | Is TotalRecalls Safe? 100% Local, Here's the Proof | ✅ complete **V2** (jasper_docs, 14,468 chars) — V1 (9,822) was truncated mid-Production-Notes, superseded |
| 9 | Free Tier vs Pro: What You Get for $24 | ❌ MISSING |
| 10 | Protect Your Conversations While You Can (Short) | ❌ MISSING |

## Email (25)

Three sequence *systems*, each with variants:

**Sequence 1 Core Welcome/Onboarding**: 2 versions (023c3cc4 byte-identical to 5d9c45c2 — delete one) + 2 stray "Email Sequence" docs (628/604 chars, early fragments)

**Sequence 2 Free-Tier→Pro Upgrade**: 2 versions (8342957e, 8a1c53b5)

**Sequence 3 Launch Urgency**: 2 versions (1c96a5a3, ddc11277)

**Email 2–4 slot variants** (A/B material): Email 2 ×5, Email 3 ×5, Email 4 ×3

(Feature Spotlight, 48 hours left, Why $24 once beats $10/mo, Still on the fence ×2,

Ownership, No cloud no account, Last call ×2, Unlock all 8 ×2, Upgrade Offer)

Sequence 2/3 **multi-email**: the numbered Email 2/3/4 docs are single emails; the

"Sequence N" docs contain only Email 1 of each sequence — **Emails 2–4 of Sequences 2 & 3

may be covered by the Email 2/3/4 docs, but that mapping was never written down**.

## Paid Ads (18)

Google Search ×2 · Google Display/PMax ×2 · Google Video ×2 · Meta ×2 · X ×3 (+1 single) ·

LinkedIn ×2 (+1 single) · Search_Ads (fc3b4b4e, overlaps Google Search?) · Ad variation 1/2/3 (generic)

## Deleted in portal 2026-09-29 (still on local disk)

User deleted all canvas docs starting with "A" to free artifact slots. Local copies remain:

`Ad_variation_1_87392ccb`, `Ad_variation_2_b37135bb`, `Ad_variation_3_4be2f2b7`

`ANDRE_DENIS_e3d925c5` (founder profile)

Also gone from the portal (and never captured locally — were virtualized nodes missed by the

one-shot capture): the audience/personas doc and any other "A" doc not in the list above.

## Organic Social (18)

Instagram captions ×4 · Facebook posts ×5 · LinkedIn posts ×4 · X/Twitter posts ×3 · Tweets ×2

→ launch-day batch only. **No provider-spotlight posts, no founder series, no urgency posts** (per gap checklists).

## Landing Page / Website (4)

Landing Page · Homepage Hero Section (921b7ea6) · Part 1 Page-by-Page Website Optimization Brief (9aede557) · Part 2 Homepage Rewrite (fb87184c)

## Messaging / Copy Assets (10)

Campaign Abstract · Headlines (ff9dd5a7) · Introducing TotalRecalls (0ac7c3d6) ·

Is TotalRecalls Safe / Windows warning answer (a9a089be) · Trust Built Differently (370c6c58) ·

Recall every AI conversation ×3 · Why I Built TotalRecalls ×2 (d7ea1339 is an earlier draft of e6cd1378)

## Launch Ops (2) · Blog (1) · Founder (1)

Launch-Day Social Posting Checklist (e23f8400) · Launch Pricing Ends Soon (674f56b2) ·

Blog Post "Why Your AI Conversations Deserve a Permanent Home" (cdd2ee9d) · ANDRE_DENIS founder profile (e3d925c5)

# 2. Holes — what the plans call for that doesn't exist

Ranked as Jasper's own Missing Items Checklist ranks them (P1 first).

## P1 — blocks launch

1. **YouTube scripts 6, 9, 10 missing** (Video 7 ✅ V3 and Video 8 ✅ V2 landed 2026-09-29;

Video 6's download was mid-generation). Remaining: #6 "Trying to Get Your Old AI

Conversations Back? Good Luck" (Short), #9 "Free Tier vs Pro: What You Get for $24",

#10 "Protect Your Conversations While You Can" (Short).

2. **Organic social program** — only launch-day posts exist. Missing: phase-aligned

weekly calendar, provider-spotlight posts for each of the 8 guides, founder-led series,

objection-handling posts, urgency-phase posts, per-platform repurposing rules.

3. **Audience / persona strategy** — both Jasper checklists (Gap Checklist, Missing Items

1.4) had it as ⬜ Open, so it may never have existed as a doc; it is not in the local

99-capture either way. Missing: 3–4 core personas with messaging angles, channel

emphasis, asset mapping.

4. **Ownership map + infrastructure verification** — process, not documents; needs a

filled-in Owner column set and a physical infrastructure test log.

5. **Email sequence completeness** — Sequences 2 and 3 have only Email 1 each as

structured documents; the Email 2/3/4 variant docs exist but are not mapped to

sequence positions. One Jasper request: "Consolidate Sequences 2 and 3 into full

4-email sequences with send timing and the variant map."

## P2 — high

6. **KPI thresholds & decision rules** — targets + "if X then Y" rules per channel/phase.

7. **Post-launch retention plan** — post-purchase onboarding, review/testimonial flow,

update communications. (Jasper has this as ⬜ Open P3 — but it's missing entirely as a doc.)

8. **Retargeting plan detail** — audiences/exclusions are defined in the master plan;

the standalone Phase 3 retargeting plan doc does not exist.

9. **Blog pipeline per 60-day calendar** — calendar schedules 12 items; existing docs:

launch announcement ✅ (0ac7c3d6), founder story ✅ (e6cd1378), category piece =

live pillar guide, urgency post ✅ (674f56b2), **8 provider-guide spotlight posts are

not blog posts in the canvas** (guides live on the website; the "spotlight" posts may

be redundant — needs a Jasper decision: publish the guides as the calendar entries

or write 8 new spotlight posts).

## P3 — medium

10. **Editorial architecture** — page roles (conversion vs SEO vs credibility),

internal linking plan, update cadence.

11. **Cross-channel publishing plan** — one master view aligning blog/social/email/ads/

video per day. The Master Implementation Plan table covers this operationally;

the "plan doc" form is thin.

12. **Source-of-truth cleanup** — 70+ overlapping assets; Jasper's own doc says the

canvas needs one approved version per slot. (Your "A"-doc deletion was step 1;

the 4 duplicate deletions recommended in REORGANIZATION.md are step 2.)

## Not holes (confirmed fine)

Provider guides (all 8) — live on the website, not in the canvas.

Headlines, campaign brief, ad copy, email variants, website briefs — complete.

Thumbnails, shot list, storyboard, upload checklist, channel description, playlists — complete.

# 3. Request list for Jasper (ready to paste)

1. **YouTube scripts 6, 9, 10** (from the 10-Video Plan): #6 "Trying to Get Your Old

AI Conversations Back? Good Luck" (Short), #9 "Free Tier vs Pro: What You Get for

$24", #10 "Protect Your Conversations While You Can" (Short). #7 and #8 are done

(V3 / V2); #6 needs regeneration — the only copy is a mid-generation download.

2. **Organic social program**: phase-aligned calendar (Phases 1–3), provider-spotlight

posts for all 8 guides, founder-led series, objection-handling posts,

launch-urgency posts, per-platform repurposing rules.

3. **Audience / persona strategy**: 3–4 core personas (developers, researchers,

writers, privacy-minded professionals), each with messaging angle, channel emphasis,

and best-fit assets. (No doc for this exists on the canvas or locally.)

4. **Email sequences consolidation**: full 4-email Sequences 2 and 3 with send timing,

mapping the existing Email 2/3/4 variant docs into their positions.

5. **KPI thresholds & decision rules**: numeric targets + pause/scale/rewrite rules

per phase and channel.

6. **Post-launch retention plan**: post-purchase onboarding sequence,

review/testimonial request flow, update communications for new providers.

7. **Blog decision**: confirm whether the 8 provider-guide "spotlight" calendar

entries are the live website guides or require 8 new posts; produce whatever

is actually missing.

# 4. Duplicates to delete (frees slots for the above)

From REORGANIZATION.md + this pass:

`TotalRecalls_Master_Implementation_Plan_26de1acc` (truncated dup)

`Sequence_1_Core_Welcome_Onboarding_023c3cc4` (byte-identical to 5d9c45c2)

`Why_I_Built_TotalRecalls_d7ea1339` (earlier draft of e6cd1378)

`TotalRecalls_Launch_Marketing_Plan_Revised_6f06cdb1` (truncated draft of 72b37216)

`YouTube_Playlist_Structure_System_for_TotalRecalls_f56207c7` (near-dup of e1aaa6d7)

Stray fragments: `TotalRecalls Welcome Email Sequence` (×3 files), `Email_Sequence_25d3ab2c`

Sequence 2/3 second versions (8a1c53b5, ddc11277) — pick one each

Ad near-dups: X_Ads ×2, Google Search ×2, Display ×2, Video ×2, Meta ×2 — keep one set per platform