# TotalRecalls Master Implementation Plan

This is your live command sheet. Where strategy tells you what to say and the gap checklist tells you what's open, this document tells you how to run the launch — every asset, on every channel, on every day, with a clear owner, CTA, dependency, and status. Treat it as the single operational source of truth for the 45-day launch window.

Fill the Owner columns with real names (or your own, if solo). Update Status daily. Everything points back to one product truth: TotalRecalls downloads your AI conversations from eight providers into local Markdown and JSON files, for a one-time $24 Pro price, with a Free Tier so people can try before they buy.

Status key: ⬜ Not started · 🟡 In progress · ✅ Done · ⏸ Blocked

Priority key: P1 Critical · P2 High · P3 Medium · P4 Low

1. Master execution table (Days -7 to 45)

Pre-launch (Days -7 to -1)

Day

Channel

Asset

Owner

CTA

KPI

Dependencies

Status

-7

Infrastructure

Blog section live + Day 1 post loaded

____

—

Blog publishes a test post cleanly

Blog template, hosting

⬜

-7

Analytics

UTM scheme + GA/events live

____

—

Test event fires end-to-end

Analytics account

⬜

-6

Website

Homepage rewrite deployed + mobile/desktop QA

____

—

Loads clean on all breakpoints

Homepage final approved

⬜

-5

Email

Platform connected, welcome sequence wired

____

—

Test signup triggers Email 1

Email tool, forms

⬜

-5

Ads

Pixels installed, ad accounts verified

____

—

Pixel fires on 3 key pages

Ad accounts

⬜

-4

Email

Segmentation tags + events created

____

—

Download and purchase events tag correctly

Email platform, tracking

⬜

-3

QA

Buy + download links tested on live site

____

—

100% of links resolve + purchase completes

Paddle/checkout live

⬜

-2

Support

SmartScreen + FAQ replies staged

____

—

Canned replies saved, owner assigned

FAQ content

⬜

-1

All

Full dry run — schedule everything

____

—

All Day 1 assets queued and previewed

All above

⬜

Phase 1 — Launch & category (Days 1–10)

Primary audience: Prospects + cold visitors. Phase CTA: Try the Free Tier.

Day

Channel

Asset

Owner

CTA

KPI

Dependencies

Status

1

Blog

Launch announcement post

____

Try the Free Tier

Page views, time on page

Blog live

⬜

1

Email

Launch broadcast + welcome Email 1

____

Try the Free Tier

Open %, click %

List, sequence wired

⬜

1

Video

Primary launch video embedded

____

Watch the demo

Views, completion %

Video file hosted

⬜

1

Paid social

Launch awareness ad set

____

Try the Free Tier

Cost per free download

Pixels, creative

⬜

1

LinkedIn

Launch organic post (9:00 AM)

____

Try the Free Tier

Reach, engagement

Blog URL live

⬜

1

X

Launch organic post (9:15 AM)

____

Try free

Impressions, reposts

—

⬜

1

Facebook

Launch organic post (10:00 AM)

____

Try the Free Tier

Reach, clicks

Blog URL live

⬜

1

Instagram

Launch post (12:00 PM)

____

Link in bio

Saves, reach

Bio link updated

⬜

5

Blog

Founder story post

____

Try the Free Tier

Views, scroll depth

Blog live

⬜

5

Social

Founder-led post (LinkedIn lead)

____

Read the story

Engagement, comments

Founder post ready

⬜

5

Email

Founder story broadcast

____

Try the Free Tier

Open %, click %

List

⬜

10

Blog

Category piece → "Own Your AI Chat Data"

____

Try the Free Tier

Views, guide clicks

Pillar guide live

⬜

10

Email

Welcome Email 2 (one library, 8 providers)

____

Try the Free Tier

Click %

Sequence wired

⬜

Phase 2 — Provider spotlights (Days 14–38)

Primary audience: Cold search + Prospects, soft nudge to Free-Tier users. Phase CTA: Try the Free Tier (mid-content Pro nudge).

Day

Channel

Asset

Owner

CTA

KPI

Dependencies

Status

14

Blog + short video

ChatGPT spotlight

____

Try the Free Tier

Organic traffic, downloads

Guide live

⬜

18

Blog + short video

Claude spotlight

____

Try the Free Tier

Organic traffic, downloads

Guide live

⬜

20

Email

Guide roundup #1 (ChatGPT + Claude)

____

Try the Free Tier

Click %

Two guides live

⬜

22

Blog + short video

Perplexity spotlight

____

Try the Free Tier

Organic traffic, downloads

Guide live

⬜

26

Blog + short video

Gemini spotlight

____

Try the Free Tier

Organic traffic, downloads

Guide live

⬜

28

Email

Guide roundup #2 (Perplexity + Gemini)

____

Try the Free Tier

Click %

Two guides live

⬜

30

Blog + short video

Grok spotlight

____

Try the Free Tier

Organic traffic, downloads

Guide live

⬜

34

Blog + short video

DeepSeek spotlight

____

Try the Free Tier

Organic traffic, downloads

Guide live

⬜

36

Email

Guide roundup #3 (Grok + DeepSeek) — Free-Tier nudge

____

Upgrade to Pro

Free→Pro clicks

Two guides live

⬜

38

Blog + short video

Mistral spotlight

____

Try the Free Tier

Organic traffic, downloads

Guide live

⬜

Phase 3 — Urgency & conversion (Days 42–45)

Primary audience: Free-Tier users + warm retargeting pools. Phase CTA: Buy Pro — $24 one-time.

Day

Channel

Asset

Owner

CTA

KPI

Dependencies

Status

42

Blog

Urgency post ("Launch Pricing Ends Soon")

____

Buy Pro — $24

Purchases

Blog live

⬜

42

Email

Urgency Email 1 (heads-up)

____

Buy Pro — $24

Conversion %

Buyer exclusion synced

⬜

42

Paid social

Retargeting urgency ad set live

____

Buy Pro — $24

ROAS, CPA

Warm pools built

⬜

43

Email

Urgency Email 2 (48 hours left)

____

Buy Pro — $24

Conversion %

Buyer exclusion synced

⬜

45

Email

Urgency Email 3 (last call)

____

Buy Pro — $24

Conversion %

Buyer exclusion synced

⬜

45

Blog + short video

Qwen spotlight (closes series)

____

Try free / Buy Pro

Traffic, downloads

Guide live

⬜

Section takeaway: If a row has no owner or an unmet dependency, it's not ready to ship. Scan this table each morning and clear blockers before publishing.

2. Asset-to-channel mapping (final vs. backup)

You have many overlapping assets on the canvas. This map designates one approved final per slot and keeps the rest as labeled backups, so nothing ships by accident.

Homepage / landing

Slot

Approved final

Backups / drafts

Channel

Homepage

TotalRecalls Homepage Rewrite

Landing Page (x4), Landing Page Hero

Website

FAQ block

FAQ (Frequently Asked Questions)

—

Website

Email sequences

Stage

Approved final

Backups / drafts

Trigger

Welcome (prospect)

TotalRecalls Welcome Email Sequence

Email Sequence (x2)

New signup

Value nurture

AI Providers Consolidation Email; Data Ownership Email Campaign

Multi-AI Organization, AI Consolidation, Privacy Features, Data Privacy

Post-welcome drip

Free→Pro upgrade

Free-to-Pro Upgrade Email Sequence

Pro Upgrade Email (x2), One-Time Payment Value (x2), Pro Upgrade Persuasion (x2), Free-Tier to Pro

Free-tier tag applied

Urgency (Phase 3)

Launch Pricing Urgency Email Sequence

Launch Urgency Sequence, Pro Launch Price Reminder, Final Reminder, Discount Reminder, Expires Tonight

Day 42

Ads

Channel

Approved final

Backups / drafts

Google/Search

TotalRecalls Search Ads

Google Ads Campaign (x2), App Google Ads, Chats Backup Google Ads, Search Campaign, Google Ads Video

Meta/Facebook

TotalRecalls Meta Ad Variations

Stop Losing AI Chats FB Ad, Social Media Ad, Ad Campaign (x2)

LinkedIn

TotalRecalls LinkedIn Ad Variations

LinkedIn Ad, Product LinkedIn Ad

X

TotalRecalls X Ads

AI Chat Backup X Ad, X Ad

Organic social

Platform

Approved final (launch day)

Backups / drafts

LinkedIn

AI Chat Backup LinkedIn Post

AI Chat Backup Tool LinkedIn Post

Facebook

TotalRecalls Facebook Post

Data Privacy FB Post, Ad Variation FB Post

X

TotalRecalls AI Chat Backup X Post

—

Instagram

TotalRecalls Product Launch IG Post

AI Privacy IG Post

Multi-platform set

Launch-Day Social Posting Checklist (Social Media Posts)

Social Media Posts (earlier versions)

Blog

Post

Approved final

Status

Launch announcement

TotalRecalls Launch Announcement Blog

✅

Founder story

TotalRecalls Founder Story Blog

✅

Category piece

Own Your AI Chat Data (live guide)

✅

Urgency post

TotalRecalls Launch Pricing Urgency Blog

✅

Governance rule: Rename every non-final asset with a [BACKUP] or [DRAFT] prefix. Only the approved final feeds the execution table. Deprecate untitled documents.

Section takeaway: One approved asset per slot. Everything else is clearly labeled and out of the shipping path.

3. Lifecycle automation logic

Three buckets carry the campaign. Every contact sits in exactly one, and actions move them between buckets automatically.

Bucket definitions and triggers

Bucket

Enters when

Primary CTA

Receives

A — Prospect

Submits any signup form; no download

Try the Free Tier

Welcome sequence, value nurture, guide roundups

B — Free-Tier user

Free-tier download event fires

Upgrade to Pro — $24

Upgrade sequence, soft Pro nudges

C — Buyer

Purchase event fires

None commercial

Onboarding, tips, feature/provider updates

Movement and suppression rules

Rule

Logic

Prospect → Free-Tier

Download event applies "free-tier" tag; remove from prospect acquisition drip

Free-Tier → Buyer

Purchase event applies "buyer" tag; exit all upgrade + urgency flows immediately

Prospect → Buyer (direct)

Purchase event applies "buyer" tag; skip free-tier flows

Buyer suppression

Exclude Bucket C from every sell, upgrade, and urgency send — no exceptions

Mid-sequence purchase

Nightly sync removes new buyers from active urgency emails before the next send

Inactive free-tier

No download activity in 14 days → "activation reminder" branch (how-to, not sell)

Unsubscribe

Global suppression across all flows; keep only transactional/license emails

Sequence entry/exit map

Welcome sequence: Entry = new signup. Exit = download (→ upgrade flow) or purchase (→ onboarding).

Value nurture: Entry = welcome sequence complete, still a prospect. Exit = download or purchase.

Upgrade sequence: Entry = free-tier tag. Exit = purchase or end of sequence (→ long-term nurture).

Urgency sequence: Entry = Day 42 for Buckets A + B. Exit = purchase or campaign end. Buyers hard-excluded.

Onboarding: Entry = purchase. No commercial CTA; focus on activation and updates.

Section takeaway: Tag on action, move on action, and suppress buyers everywhere. The nightly buyer sync is the single most important automation to get right.

4. Retargeting mechanics

Phase 1–2 builds the pools; Phase 3 converts them. Set these up early so audiences are large enough by Day 42.

Audience definitions

Audience

Definition

Window

Pricing viewers

Visited pricing or buy page, no purchase

30 days

Download-page visitors

Visited download page, no confirmed free-tier

30 days

Free-tier users

Confirmed free-tier tag, no Pro

45 days

Video viewers

Watched 25%+ of launch or spotlight video

30 days

Guide readers

Read any Phase 2 spotlight/guide page

30 days

Exclusions (critical)

Suppress all buyers (Bucket C) from every retargeting ad set.

Sync the buyer tag to each ad platform daily so purchasers stop seeing sell ads within 24 hours.

Exclude anyone who converts mid-campaign from active urgency ad sets.

Creative rotation rules

Phase

Creative focus

Rotation

Phase 1–2 (pool-building)

Soft: loss aversion, ownership, "try free"

Rotate 2–3 creatives; refresh every 7 days

Phase 3 (conversion)

Hard: deadline + one-time-vs-subscription math

3-creative rotation; swap the fatigued unit at CTR drop >20%

Free-tier specific

"5 locked providers Pro unlocks"

Serve only to Bucket B

Activation thresholds: Don't launch a retargeting set until its audience clears platform minimums (roughly 1,000+ users). If a pool is thin by Day 40, consolidate audiences to reach size.

Section takeaway: Build pools from Day 1, cap frequency, and let the daily buyer sync protect your paying customers from sell ads.

5. Infrastructure readiness checklist

This is your pre-launch gate. If any item is unchecked, hold the launch.

Blog and website

⬜ Blog section live, template tested, headings and CTA slot working

⬜ Meta title/description fields functional

⬜ Day 1 announcement post loaded and scheduled

⬜ Homepage rewrite deployed and reviewed on mobile + desktop

Analytics and UTMs

⬜ Analytics installed and firing on all key pages

⬜ UTM convention documented (utm_source / utm_medium / utm_campaign=launch)

⬜ Free-tier download event tracked

⬜ Purchase event tracked

Email capture and platform

⬜ Signup forms live on homepage, guide pages, pricing/buy pages

⬜ "Notify me" capture for macOS/Linux and new providers

⬜ Email platform connected with tags and automations

⬜ Welcome sequence test-fires on new signup

Ad pixels

⬜ Pixels installed on homepage, pricing, download pages

⬜ Conversion events mapped (download, purchase)

⬜ Ad accounts verified and billing active

Buy/download links QA

⬜ Buy link completes a real test purchase

⬜ Free-tier download link delivers the correct ZIP

⬜ License key delivery email confirmed

⬜ All CTAs across site point to correct destinations

Support workflow

⬜ Support inbox monitored, owner assigned

⬜ SmartScreen canned reply saved

⬜ FAQ/help path reachable from every page

⬜ Escalation path defined for edge-case issues

Section takeaway: No blog, no tracking, no working buy link means no launch. Clear every box before Day 1.

6. Launch-week support and objection-handling workflow

A new downloadable Windows tool triggers predictable questions. Handle them fast and consistently.

Monitoring cadence (Days 1–7)

Window

Action

Owner

First 4 hours

Check all platforms + support inbox every 30 min

____

Hours 4–24

Check every 1–2 hours

____

Days 2–7

Check morning, midday, evening

____

Canned replies

SmartScreen warning ("Windows protected your PC"):

Thanks for flagging this! That message is standard SmartScreen behavior for any newly released, independently developed app — it's not a sign of malware. Click More info, then Run anyway to continue. Only download from totalrecalls.app. As the app builds reputation with Microsoft, the warning fades. Any trouble, email support@totalrecalls.app.

"Is my data safe / uploaded anywhere?":

Great question. TotalRecalls runs 100% locally — your conversations are saved to a folder on your own machine as Markdown and JSON, and nothing is ever uploaded to a server. There's no account and no sign-up. More detail on our Privacy Policy.

"Is this a subscription?":

No subscription, ever. Pro is a one-time $24 (discounted launch price), and you keep free updates to the core app for life. There's also a Free Tier so you can test it first.

"Does it work on Mac / mobile?":

Not yet — Windows 10/11 today. macOS and Linux versions are in development. Drop your email on our site and we'll notify you when they land.

FAQ escalation process

Tier 1 — Canned reply. Covered above? Respond with the saved reply.

Tier 2 — Personalized. New but simple? Answer directly, then log it.

Tier 3 — Escalate. Bug or edge case? Route to the developer, set expectation on timing.

Feed the loop. Any question asked 3+ times → add to the live FAQ and consider a Day 2–3 social FAQ post.

Section takeaway: Speed and consistency build trust for a new app. Pre-written replies and a clear escalation ladder keep launch week calm.

7. Testing roadmap

Test one variable at a time, give each test enough traffic to matter, and roll winners into the approved assets.

Element

What to test

How

Success metric

When

Headlines

Loss-aversion vs. ownership framing

A/B on homepage hero + top ads

Click-through to free download

Phase 1

CTAs

"Try the Free Tier" vs. "Download free"

Button-copy A/B on homepage

Download conversion rate

Phase 1

Landing variants

Homepage rewrite vs. control section order

Split traffic 50/50

Free-tier downloads per visit

Phase 1–2

Email subject lines

Curiosity vs. direct-benefit

A/B on each broadcast

Open rate

Every send

Ad creatives

Static graphic vs. short video

Per-platform creative A/B

Cost per free download

Phase 1–2

Urgency framing

Deadline-led vs. value-led

A/B on Phase 3 ads + emails

Purchase conversion rate

Phase 3

Testing rules

Change one variable per test — never headline and image together.

Let each test run to a meaningful sample before calling it; don't stop early on noise.

Log every result in a shared sheet; promote winners into the approved asset for that slot.

Kill any ad creative when CTR drops more than 20% below its cohort.

Section takeaway: Small, disciplined tests compound. Feed every winner back into your approved assets so quality climbs across the whole launch.

How to run this document

Assign owners to every row